Terms of Reference

Establishing a national coordination mechanism and publish a costed roadmap with targets in I.R. Iran

Background and Rationale

Building on the situational analysis of water, sanitation and hygiene (WASH) services in healthcare facilities (HCFs) in Iran, and the baseline assessment of 730 HCFs, which established the national conditions of WASH in HCFs and embraced the first step of the “Eight Practical Steps to Achieve Universal Access to Quality Care”. The second practical step is to develop a national roadmap with a set of detailed targets which details how the country will reach those targets and address identified gaps. The roadmap will include short, medium and long-term goals and activities, clarify who is responsible for achieving these goals and importantly, how much it will cost. It also includes a plan for ongoing monitoring, review and final evaluation of the strategy’s success.

Furthermore, the road map will need to take into consideration the special needs of vulnerable groups and underserved areas and facilities, how climate change may affect progress and what can be done to mitigate these effects. It will consider levels of the health system, from the smallest facilities and clinics in remote areas to larger tertiary hospitals and other facilities providing specialised services. Furthermore, it sets realistic goals which are both aspirational as well as achievable within the timeframe of the strategy. Goals will need to be as specific and measurable as possible to encourage accountability and future evaluation of the strategy’s success.

Costing estimates should include costs for capital investments, rehabilitation, as well as recurrent costs associated with operation and maintenance. These costs should also include energy costs for pumping and treating water, treating waste and keeping toilets and shower areas lit. In addition, costs for supportive supervision and regular skill building (training) for all staff including managing WASH supplies, waste and/or cleaning should be assessed as part of wider quality improvement and supervision investments. Finally, related costs including development and dissemination of technical manuals, guidance, and monitoring should also be factored in.

Work to be performed

Output 1: Detailed project proposal

Following the recent baseline assessment of 730 HCFs in Iran, a summary of the situational analysis, latest data, gaps, strengths and weaknesses of health system and WASH services was developed. Furthermore, as this project involves different departments of the MOHME (such as finance) as well as other national concerned ministries and organizations (such as ministry of energy and plan and budget organizations), the team should include representatives of these different partners engaged in WASH in HCF activities, hence, a comprehensive stakeholder analysis and mapping from all relevant stakeholders needs to be provided.

Deliverable 1: Provide a detailed project proposal including summary of the results of the recent situational analysis and assessment of WASH in HCFs in Iran, and the stakeholder mapping.

Output 2: Establishing a working group

Based on the stakeholder analysis, the consultant needs to support the Ministry of Health and Medical Education (MOHME) to establish a national working group with the support of WHO. The national working group would be led by the MOHME and would include decision-makers from relevant ministries as well as technical staff and partners engaged in WASH in HCF activities. Furthermore, define a detailed terms of reference and membership roles of the working group to help set the targets, develop the roadmap, estimate the costs, provide technical and political support, and coordinate implementation efforts.

Deliverable 2: Provide a report on establishment of the working group, with a detailed terms of reference for the members, and the joint meeting plans.

Output 3: Thorough analysis of the relevant strategies available in the health sector towards a drafted road map

Conducting a thorough study and analysis and provide a context and legal framework for WASH in HCFs, a framework for sustainable implementation of national guidelines and standards for WASH in HCFs at all levels, seek to integrate WASH in HCFs into any existing monitoring systems within the MOHME, and encourage better integration between WASH and health initiatives nationally and locally. All in consideration of key laws, legislation, policies and standards relevant for WASH in HCFs and how are they tied to the strategy.

Deliverable 3: Draft of the road map based on a thorough analysis of current strategies and frameworks and joint meetings with stakeholders

Output 4: Finalizing the costed road map in agreement with all stakeholders

The drafted road map needs to be reviewed by all stakeholders and evaluated in terms of cost estimations. The main considerations for the costs include:

- Human resources and their trainings.

- For capital investments:

- construction, installation, drilling or purchasing pumps, pipes, toilets, urinals, basins and other hand washing facilities, bins etc.

- demolition, disposal and replacement of facilities that are beyond repair and/or beyond their intended lifespan,

- major repairs and rehabilitation, including climate-related upgrades;

- For recurrent/operation and maintenance costs:

- fees for water, electricity and waste collection

- emptying of sludge/septage from septic tanks, latrines and other sludge holding chambers

- purchase of consumables such as soap, alcohol-based hand rub etc.

- purchase of cleaning materials such as mops, brushes, buckets, detergents etc.

- salaries for cleaners, janitors or health care waste staff

- hiring technical support services including plumbers, carpenters, masons, electricians etc. for minor repairs

- costs of hygiene promotion for staff, patients, family members etc. who use the facility as workers, patients or caregivers.

Furthermore, the road map needs to be sustainably implemented. Therefore, monitoring and evaluation (M&E) time-bound plan, responsible entities for data collection, data analysis, dissemination of the results, M&E reporting are needed. Also, short, medium, and long term implementation milestones need to be identified for M&E.

Deliverable 4: Finalized costed road map, final report and an executive summary on the whole project, including stakeholder engagement, committee meetings, undertaken procedures, technical methodologies, and results

Note: All deliverables should be full in both English and Farsi.

|  | Deliverable/Phase | Due date (2022) | % of total payment |
| --- | --- | --- | --- |
| 1 | Provide a detailed project proposal including summary of the results of the recent situational analysis and assessment of WASH in HCFs in Iran, and the stakeholder mapping. | 15 August | 25% |
| 2 | Provide a report on establishment of the working group, with a detailed terms of reference for the members, and the joint meeting plans. | 1 October | 20% |
| 3 | Draft of the road map based on a thorough analysis of current strategies and frameworks and joint meetings with stakeholders | 1 November | 25% |
| 4 | Finalized costed road map, final report and an executive summary on the whole project, including stakeholder engagement, committee meetings, undertaken procedures, technical methodologies, and results | 30 November | 30% |

Specific requirements

Characteristics of the project manager:

- Qualifications required:

Essential: First university degree in environmental health studies

Desirable: PhD degree in relevant fields

- Experience required:

- Over 7 years of experience working in environmental health, studies or relevant field

- Previous experience and projects relevant to WASH in HCFs

- Previous work experience with WHO/UN

- Skills / Technical skills and knowledge:

Excellent presentation and communication skills.

Excellent leadership and coordination skills

- Language requirements:

Fluent in English (Read-Write-Speak)

Characteristics of the institute (service provider):

- Status

The provider shall be an institution operating in the field of environmental health with proven expertise in project management of projects in the area of WASH in HCFs.

- Previous experience

Previous work with WHO, other international organizations and/or major institutions in the field of WASH in HCFs. Include the resume of the provider.

- Staffing

The provider must introduce their team of experts who will implement the project along with their credentials/CVs.

- Place of assignment

I. R. Iran

- Travel N/A

The Consultant is not expected to travel

https://www.who.int/publications/i/item/9789241515511